THE PETROLEUM & NATURAL GAS REGULATORY BOARD

NOTIFICATION
New Delhi, the29th March, 2016

F.No.VKS/DB/03/PPL.- In exercise of the powers conferred by section 61 of the Petroleum and Natural Gas Regulatory Board Act, 2006 (19 of 2006), the Petroleum and Natural Gas Regulatory Board hereby makes the following regulations, namely:-

1.   Short title and commencement:

(1) These regulations may be called the Petroleum and Natural Gas Regulatory Board (Authorizing Entities to Lay, Build, Operate or Expand Petroleum and Petroleum Products Pipelines) Amendment Regulations, 2016.

(2) They shall come into force on the date of their publication in the Official Gazette.

2.   In the Petroleum and Natural Gas Regulatory Board (Authorizing Entities to Lay, Build, Operate or Expand Petroleum and Petroleum Products Pipelines) Regulations, 2010, -

(a) in regulation 13, -

(i)
for sub-regulation (1), the following shall be substituted, namely:-

“(1) a authorized entity shall provide, on a monthly and quarterly basis, a progress report detailing the clearances obtained, targets achieved, expenditure incurred, works-in- progress and other relevant information in the forms at Schedule E as per formats E-1A- PPL, E-1B-PPL for quarterly reports and E-2-PPL for monthly report.”;

(ii)
after sub-regulation (4), the following sub-regulation shall be added, namely:-

“(5) a authorized entity shall designate an official of the entity for submitting data / information to the Board and intimate the same to the Board. Any change in the designated official shall be communicated to the Board by the authorized entity within 7 working days.”;

(b) in regulation 14, after sub-regulation (8), the following sub-regulation shall be added, namely:-

“(9) a authorized entity shall continue to submit post commissioning information / data in the forms at Schedule E as per formats E-1A-PPL, E-1B-PPL for Quarterly reports and E-2-PPL for monthly report.”;

(c) for Schedule E, the following shall be substituted, namely:-

“Schedule E
[see regulation 13 (1) and regulation 14 (9)]

A: Quarterly submission of data by authorized entity in the following formats appended here below:-

(i)
Format E-1A-PPL for Quarterly Progress Report on CGD: Physical Parameters

(ii)
Format E-1B-PPL for Quarterly Progress Report on CGD: Financial Parameters

B: Monthly submission of data by authorized entity in the following format appended here below:-

(i)
Format E-2-PPL for Monthly Report on Petroleum Pipeline Throughput

C: The data and information required to be submitted by the entity in the above formats shall be analyzed by the Board by comparing the –

(i)  actual progress made by the entity including commissioning of the project versus the physical and financial targets, identified in its DFR; and

(ii) actual volume of petroleum products transported in the petroleum and petroleum

products pipeline versus the volume committed in the bid.

D: Monitoring of the progress shall be taken up by the Board on a quarterly basis and the notice of deviations and shortfalls, if any, shall be sent to the entity for a prompt resolution. In case of any delay in meeting the yearly commitments within the notice period or in case of repeated violations, the entity may face the consequences specified under regulation 16 of the Petroleum and Natural gas Regulatory Board (Authorizing Entities to Lay, Build, Operate or Expand City or Local Petroleum and Petroleum Products Pipelines) Regulations, 2010.

Appended Formats:

	Schedule-E / Format: E-1A-PPL
	Quarterly Progress Report on Petroleum Pipelines: Physical Parameters

	1. Name of Entity
	

	2. Project Name
	

	3. Report for the Quarter ending
	
	4. Year
	

	
	7. Quarter
	8. Cumulative (since inception)

	5. Petroleum Pipeline Length
	6. Diameter in inches
	Target*
	Actual
	Target
	Actual

	Diameter-1
	
	
	
	
	

	Diameter-2
	
	
	
	
	

	Diameter-3
	
	
	
	
	

	Diameter-4
	
	
	
	
	

	Diameter-5
	
	
	
	
	

	9. No. of Pumping Stations, Intermediate terminals & delivery terminals
	Target*
	Actual
	Target
	Actual

	Pumping Stations
	
	
	
	

	Intermediate Delivery Stations
	
	
	
	

	Delivery Terminals
	
	
	
	

	10. project completion status- Actual versus Approved Target (%)
	Target%*
	Actual%
	Target
	Actual

	(Not Applicable for already commissioned pipelines)
	
	
	
	

	11. Design Capacity (MMT)

	Existing capacity
	

	Added during the quarter
	

	Total at the end of quarter
	

	12. Any other information (Please write in the box)

	

	* Target figures may be given wherever applicable.  Quarterly target may be taken as 1/4th of annual target.

	13. Important guidelines for submitting the report:

	(1) In case data is nil for any of the columns; please enter zero '0' (2) Report must be submitted within 30 days from the close of Quarter.(3)  A scanned copy of the report stamped & signed by a person of General Manager or above rank, duly authorized by Director of the company, should be uploaded within 10 days from date of submitting the report online as per instructions given for uploading the report.

	14. Note: Please note that due to technical reasons, the information sought in columns / rows may have to be rearranged as required while implementing the online reporting system.


	Schedule-E / Format: E-1B-PPL
	Quarterly Progress Report on Petroleum Pipelines: Physical Parameters

	1. Name of Entity
	

	2. Project Name
	

	3. Ownership Details
	Name
	
	Share%
	

	
	Name
	
	Share%
	

	
	Name
	
	Share%
	

	
	Name
	
	Share%
	

	4. Report for the Quarter ending
	                                   5. Year
	

	All figures to be submitted in Lacs Rupees unless specified otherwise

	Capital Investments

	6. Fixed Assets
	12. Revenue Earned

	Opening balance
	Transmission of Petroleum Products

	Direct additions
	Other income

	Transfer from Capital Work-in- Progress
	
	Total Revenue
	

	Deletions / Transfers
	
	13. Profit/Loss

	Closing Balance
	
	Profit before tax
	
	

	7. Capital Work-in-Progress (CWIP)
	
	Tax
	

	Opening balance
	
	Profit after tax
	

	Additions
	
	14. Loans Status

	Transfer to fixed assets
	
	(a) Term Loans
	
	

	Deletions / Transfers
	
	Opening balance
	
	

	Closing balance
	
	Added during quarter
	

	8. Operating Expenses
	
	Repaid during Qtr.
	

	Cost of goods sold
	
	Closing balance
	
	

	Utilities - Power and Fuel
	
	Average Interest Rate (%)
	

	Salaries
	
	(b) Working Capital Loans
	

	Repair and maintenance
	
	Opening balance
	
	

	Gen. administrative expenses
	
	Added
	
	

	Insurance
	
	Repaid
	
	

	Others
	
	Nett change
	
	

	9. Financial Expenses
	Average Interest Rate (%)
	

	Interest on Working capital borrowings
	
	15. Any other information (Please write in the box)

	Interest on term loans
	
	

	10. Depreciation
	
	

	11. Total Expenses
	
	

	16. Important guidelines for submitting the report:

	(1) In case data is nil for any of the columns; please enter zero '0' (2) Report must be submitted within 60 days from the close of Quarter.   (3)   A scanned copy of the report stamped & signed by a person of General Manager or above rank, duly authorized by Director of the company, should be uploaded within 10 days from date of submitting the report online as per instructions given for uploading the report. (4) Annual report for the year-end (4th Quarter) should be submitted duly certified by a Chartered Accountant (CA) (5) Please ensure that sum total of figures submitted for four quarters of the year is equal to the company's audited annual data.

	17. Note: Please note that due to technical reasons, the information sought in columns / rows may have to be rearranged as required while implementing the online reporting system.


	Schedule-E / Format: E-2-PPL
	Monthly Report on Petroleum Pipeline Throughput

	1. Name of Entity
	

	2. Project Name
	

	3. Month
	
	4. Year
	

	5. Length (Kilometers)
	
	6. Design Capacity (MMT)
	

	7. Months


	8. Pipeline Throughput Data (in MMT up to 3 decimals)
	9. Cum. Capacity Utilization (%)

	
	Monthly
	Cumulative
	

	April
	
	
	

	May
	
	
	

	June
	
	
	

	July
	
	
	

	August
	
	
	

	September
	
	
	

	October
	
	
	

	November
	
	
	

	December
	
	
	

	January
	
	
	

	February
	
	
	

	March
	
	
	

	10. Any other information (Please write in the box)

	11. Important instructions for submitting report:

	(1) In case data is nil for any of the columns for the month. Please enter zero ‘0’ (2) Report must be submitted by 20th of the following month (3) A scanned copy of the signed & stamped report must be uploaded within 7 days from the date of submitting the report online as per instructions given for uploading the report.

	12. Note: please note that due to technical reasons, the information sought in columns/rows may have to be rearranged as required while implementing the online reporting system. 


UPAMANYU CHATTERJEE, Secy.
[ADVT.-III/4/Exty./418]
Footnote: Principal regulations were notified vide GSR 722 (E) dated 01/09/2010 and amended vide F. No. L-MISC/VI/I/2007 dated 01/01/2015.


